# Check of the Attack and Dataset Validation Basis

Checked file: Plan/Paper-Editing/4-Verification/Attack-and-Dataset-Validation-Basis.docx (dated Oct 14, 2026; byte-identical to the copy in 3-Guides/). Checked on: oct. 20, 2026, against verify_attack.py run on every campus run, the run inventory, the source PDFs in Resources/, the current paper (v2) and the deviation log.

Verdict: the structure and the reasoning are sound and match the paper, but the document is a snapshot of Oct 14. It has 6 wrong claims, 13 out-of-date numbers or references, and 1 claim that could not be checked. Fix the "Wrong" rows before anyone quotes it; the "Outdated" rows need the Oct 20 numbers.

# 1. What is correct

- The three-layer approach and the 300 / 180 / 120 s timeline with each run as its own control.

- Airehrour et al.: 14 motes, smart building, 2 blackhole motes, 60–75% loss, 16–246 rank changes, blackhole = false low rank then discard (checked against the PDF on oct. 19).

- Both conformance tables (blackhole and wormhole), including the two criteria stated as not met.

- The run-time assignment of the wormhole ends by depth (D-17), roles locked at the first phase, no victims in a wormhole run.

- Wormhole, DLSU Library linear stationary: Node A layer 5, Node B layer 7; all 181 Node B probes twice; none in baseline or cooldown; median gap 2.8 ms, 90% within 6.5 ms. Today's verifier also passes this run (duplicates in 180 attack windows).

- Zhukabayeva's 3-sigma test, the out-of-band tunnel, and the route-change numbers 80–100 → 120–200 ms and 20–30% modified.

- Ramírez Gómez: duplicated routing packets, two per data packet, as a proposed signature.

- Integrity rules: 95% coverage per board, 1 s windows with 8 of 10 samples, last 300 s of phase 0 as baseline, HT20 only.

- Keeping time-in-run out of model inputs because there is no jitter.

# 2. Claims to fix

| # | Where | The guide says | What the evidence shows | Verdict | Fix |
| --- | --- | --- | --- | --- | --- |
| 1 | Blackhole layer 2 example; layer 3 table; Exhibit 2 text | G402 linear stationary: attacker ForwardingRatio 0.995 → 0.000, child PDR 0.938 → 0.238, "about 76%" loss | verify_attack.py today: ForwardingRatio 1.000 → 0.001 (forwarded 1 of 1,077); all six victims PDR 1.000 → 0.000. Loss is 100%, above the 60–75% range | Wrong | Use 1.000 → 0.001, six victims 1.000 → 0.000, loss 100% ("above the published range: every routed probe is lost") |
| 2 | Status on Oct 14; Design; panel table; limits | 46 captured, 24 of 84 done (23 + 1); 72 attack + 12 benign = 84 runs | Design is now 72 + 9 benign = 81 runs, no jitter (team decision). Oct 20: 44 processed (35 blackhole + 9 wormhole), 0 of 9 benign | Outdated | Replace with the Oct 20 status, or keep the Oct 14 snapshot but change 84 → 81 and 12 → 9 |
| 3 | Sources table (Ramírez Gómez); Exhibit 10 | "A wormhole built with XBee ZigBee nodes and an out-of-band link"; "two nodes joined by an out-of-band link" | Source PDF: one malicious node "M" between S and D builds the tunnel; two linked malicious nodes are only mentioned as an option from another paper. Their Figure 2 is "Wormhole attack with malicious node"; the test setups are Figures 7 and 8 | Wrong | "A wormhole built with a single malicious node on an XBee ZigBee network"; Exhibit 10 → "Wormhole attack with a malicious node, adapted from [72, Figure 2]" |
| 4 | Exhibit 7; wormhole layer 3 | Exhibit 7 "Changes in network parameters under a wormhole attack [71, Table 7]" | Table 7 of the source is titled "Software components of WSN nodes"; the numbers (80–100 → 120–200 ms, 20–30% modified) are its route-change row and are right. "+40%" and ">30%" come from the abstract | Wrong | Cite "[71, Table 7, route-change row]" and keep the abstract figures apart from the table figures |
| 5 | Sources table (Zhukabayeva); blackhole layer 3 "Node behaviour"; Exhibit 9; reason 4 | "Sinkhole event log [71, Table 4]" as "the closest published record" of our blackhole | The real title is "Pre-attack and post-attack transmission logs", and it comes from their simulation, not their hardware testbed | Wrong | Use the real title and say it is simulated |
| 6 | Sources table (Khan); Exhibit 4; smart-campus table | Healthy delivery "96.5 to 99.1%"; "sampled every 2 minutes" | The paper says above 97% at every node except node H. The Khan PDF is not in Resources/, so 96.5–99.1% could not be checked. The 2-minute interval is for sensor readings; the delivery figures come from a 60 s, five-day stability test (oct. 19 report) | Unverified | Check Khan Figure 20 and use one figure in both the guide and the paper; fix the sampling sentence |
| 7 | Known data-quality items | "Highload at seven boards can collapse the mesh even without an attack" | That was the root logging arrivals too slowly (fixed Oct 7); every campus highload blackhole run after the fix recovers fully in cooldown (oct. 19 report, must-fix 2). The paper no longer calls highload a testbed limit | Wrong | "Early highload captures lost arrival rows at the root; fixed on Oct 7 and recaptured" |
| 8 | Smart-campus table, "Topologies" row | Linear = corridor, star = room, tree = stairwell, partial = atrium "(thesis Table 4.14)" | The paper (§4.2.2.5) now says the four topologies are logical layouts, not tied to kinds of place, and are set up at every site. Table 4.14 is now "Local Storage Architecture" | Outdated | Drop the mapping or agree it with the team; it contradicts the paper |
| 9 | Exhibit 1 text; "What the scenario does not claim" | "one attacker and seven boards"; "Seven boards" | Every campus run has 8 boards: the root and 7 children (inventory) | Wrong | Seven → eight |
| 10 | Reason 5 | Deviations log "D-1 to D-19" | The log now runs to D-32 | Outdated | D-1 to D-32 |
| 11 | Sources table (Hu et al.) | Wormhole criteria "in Table 4.18" | They are in Table 4.5 of the paper | Outdated | Table 4.5 (blackhole criteria are Table 4.4) |
| 12 | Dataset design | "Each run has a 60 s formation period" | Formation lasts at least 60 s and continues until the pre-run gates pass and the operator types START (D-22, D-24, D-27) | Outdated | "at least 60 s, until START" |
| 13 | Wormhole limits; panel table; "What this does not mean" | Wormhole checked "in one" linear run; 1 of 36 done | 9 linear wormhole runs (every site and scenario) PASS the verifier; none yet on star, tree or partial mesh | Outdated | Update the counts and keep the "linear only" limit |
| 14 | Single-feature audit | 38 analysed runs; PDR and LatencyHopRatio ≥ 0.95 in 11 runs, ForwardingRatio and ConsistencyScore in 8 | The paper quotes the Oct 15 audit: 34 runs, 12 and 9 (reproduced in the oct. 19 check). The 38-run figures could not be traced | Outdated | Use the paper's dated 34-run figures so the two documents agree |
| 15 | Blackhole layer 2, DLSU Library linear jitter example | ForwardingRatio 0.997 → 0.000; received 806, dropped 806; baseline 1751 received / 1751 forwarded | Pattern is right (4 victims 1.000 → 0.000, 2 bystanders stay at 1.000). After the Oct 19 re-analysis: ForwardingRatio 1.000 → 0.000; attack 805 received, 805 dropped; baseline 1,551 received, 1,550 forwarded. Jitter is also outside the study design now | Outdated | Update the numbers and say it is a jitter run outside the 81-run design, or use a stationary run instead |
| 16 | Known data-quality items | "Two G402 tree runs lost boards and also need a second run" | Both were recaptured: tree/G402/stationary (Oct 18) and tree/G402/burst (Oct 19, PASS) | Outdated | Remove, or say recaptured |
| 17 | Known data-quality items | "About 16 captured runs are off the plan" | The inventory now shows 3 off-plan cells (home runs) | Outdated | Update the count |
| 18 | Wormhole layer 2 | Auto-switch host test 35 of 35 | The host test now has 79 cases, all passing (STATUS, oct. 20) | Outdated | Give the current count with its date |
| 19 | Sources table (Espressif) | "ESP-IDF v5.3 documents" | The firmware is built with v5.5.4 and v5.3.5 (run logs) | Outdated | Name the versions actually used |
| 20 | Blackhole "did not reproduce" | Retransmissions not observed; retry counters are application counters | Correct reason, but the evidence for "not observed" should be the sniffer's MacRetryRate (D-15); those sniffer columns are currently missing from 20 runs and must be recomputed | Outdated | Cite the sniffer result once it is recomputed |

# 3. Could not be checked here

- "Counters recomputed by hand from raw files … match the tools" — no record of the manual check was found in the repository.

- "window_start alone scored 0.857" — not reproduced here.

- Zhan et al. [73] (REAL-IoT) and Abdallah et al. [74] — the guide itself says they were not re-opened.

# 4. Suggested next step

Correct the guide in 3-Guides/ (the copy members are told to read), then delete or replace the duplicate in 4-Verification/ so only one version circulates. The paper (v2) already carries the corrected numbers for rows 1, 3, 4, 7, 9, 10, 12 and 19; row 5 (the sinkhole table title) is still open in the paper too.